## Year 1
| Unit | Total | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
RECEIPTS |  |  | April | May | June | July | August | September | October | November | December | January | February | March
|  |  | 18.08 | 12.05 | 6.03 | 6.03 |  |  |  |  | 8.26 | 8.26 | 16.52 | 24.78
Harvested timber - spruce sawlogs |  | 53014.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53014.5 | 0 | 0 | 0 | 0
Harvested timber - spruce local firewood |  | 15708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15708 | 0 | 0 | 0 | 0
Harvested timber - spruce chipwood |  | 117810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117810 | 0 | 0 | 0 | 0
FGS - long term plan production |  | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0
TOTAL RECEIPTS |  | 188732.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 186532.5 | 0 | 0 | 0 | 0
PAYMENTS
Direct Costs
Improve junction with A861 |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0
Form new access and bell mouth at forest access to Longrigg Road |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0
Access track - from Longrigg Road to new turning/stacking area in wood and woodlots. |  | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0
Turning and timber stacking area in woodland |  | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0
Fence repairs |  | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0
Indirect costs
Professional fees |  | 3300 | 400 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 700 | 0 | 0 | 0
Insurance |  | 960 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
TOTAL PAYMENTS |  | 72260 | 480 | 80 | 80 | 80 | 80 | 2280 | 80 | 67080 | 780 | 80 | 1080 | 80
NET CASH FLOW |  | 116472.5 | -480 | -80 | -80 | -80 | -80 | -2280 | 2120 | 119452.5 | -780 | -80 | -1080 | -80
OPENING BALANCE |  |  | 0 | -480 | -560 | -640 | -720 | -800 | -3080 | -960 | 118492.5 | 117712.5 | 117632.5 | 116552.5
CLOSING BALANCE |  | 116472.5 | -480 | -560 | -640 | -720 | -800 | -3080 | -960 | 118492.5 | 117712.5 | 117632.5 | 116552.5 | 116472.5
VAT |  | Total | April | May | June | July | August | September | October | November | December | January | February | March
Due on sales |  | 34950.3 | February: 34950.3
Reclaim on purchases |  | 13400 | February: 13400
Note on D21: Will Richardson: Insert opening bank balance

## Year 2
| Unit | Total | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
RECEIPTS |  |  | April | May | June | July | August | September | October | November | December | January | February | March
|  |  | 18.08 | 12.05 | 6.03 | 6.03 |  |  |  |  | 8.26 | 8.26 | 16.52 | 24.78
Harvested timber - larch local firewood - removal of 10% of trees (thin or clearfell) |  | 8701.2926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8701.2926 | 0 | 0 | 0 | 0
TOTAL RECEIPTS |  | 8701.2926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8701.2926 | 0 | 0 | 0 | 0
PAYMENTS
Direct Costs
Road and track repairs |  | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0
Maintenance |  | 1564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564 | 0 | 0 | 0 | 0
Replanting |  | 15523.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15523.2
Site prep - scarifying |  | 5550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5550 | 0 | 0
Indirect costs
Professional fees |  | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 700 | 0 | 700 | 0
Insurance |  | 960 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
TOTAL PAYMENTS |  | 55697.2 | 80 | 80 | 80 | 80 | 80 | 80 | 780 | 1644 | 30780 | 5630 | 780 | 15603.2
NET CASH FLOW |  | -46995.9074 | -80 | -80 | -80 | -80 | -80 | -80 | -780 | 7057.2926 | -30780 | -5630 | -780 | -15603.2
OPENING BALANCE |  |  | 116472.5 | 116392.5 | 116312.5 | 116232.5 | 116152.5 | 116072.5 | 115992.5 | 115212.5 | 122269.7926 | 91489.7926 | 85859.7926 | 85079.7926
CLOSING BALANCE |  | 69476.5926 | 116392.5 | 116312.5 | 116232.5 | 116152.5 | 116072.5 | 115992.5 | 115212.5 | 122269.7926 | 91489.7926 | 85859.7926 | 85079.7926 | 69476.5926
VAT |  | Total | April | May | June | July | August | September | October | November | December | January | February | March
Due on sales |  | 435.0646 | February: 435.0646
Reclaim on purchases |  | 6512.8 | May: 200; February: 6312.8

## Year 3
| Unit | Total | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
RECEIPTS |  |  | April | May | June | July | August | September | October | November | December | January | February | March
|  |  | 18.08 | 12.05 | 6.03 | 6.03 |  |  |  |  | 8.26 | 8.26 | 16.52 | 24.78
FGS woodland improvement Spruce clearfell compartments only |  | 21835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21835
TOTAL RECEIPTS |  | 21835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21835
PAYMENTS
Direct Costs
Maintenance |  | 3116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116 | 0 | 0 | 0 | 0
Indirect costs
Professional fees |  | 575 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 175
Insurance |  | 960 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
TOTAL PAYMENTS |  | 4651 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 3196 | 80 | 80 | 80 | 255
NET CASH FLOW |  | 17184 | -80 | -80 | -80 | -80 | -80 | -480 | -80 | -3196 | -80 | -80 | -80 | 21580
OPENING BALANCE |  |  | 69476.5926 | 69396.5926 | 69316.5926 | 69236.5926 | 69156.5926 | 69076.5926 | 68596.5926 | 68516.5926 | 65320.5926 | 65240.5926 | 65160.5926 | 65080.5926
CLOSING BALANCE |  | 86660.5926 | 69396.5926 | 69316.5926 | 69236.5926 | 69156.5926 | 69076.5926 | 68596.5926 | 68516.5926 | 65320.5926 | 65240.5926 | 65160.5926 | 65080.5926 | 86660.5926
VAT |  | Total | April | May | June | July | August | September | October | November | December | January | February | March
Due on sales |  | 0
Reclaim on purchases |  | 4837.84 | May: 4214.64; February: 623.2

## Year 4
| Unit | Total | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
RECEIPTS |  |  | April | May | June | July | August | September | October | November | December | January | February | March
|  |  | 18.08 | 12.05 | 6.03 | 6.03 |  |  |  |  | 8.26 | 8.26 | 16.52 | 24.78
Harvested timber - pine local firewood - removal of 10% of trees (thin or clearfell) |  | 10152.9839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10152.9839 | 0 | 0 | 0 | 0
TOTAL RECEIPTS |  | 10152.9839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10152.9839 | 0 | 0 | 0 | 0
PAYMENTS
Direct Costs
Maintenance |  | 3116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116 | 0 | 0 | 0 | 0
Indirect costs
Professional fees |  | 750 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 350 | 0 | 0 | 0 | 0
Insurance |  | 960 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
TOTAL PAYMENTS |  | 4826 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 3546 | 80 | 80 | 80 | 80
NET CASH FLOW |  | 5326.9839 | -80 | -80 | -80 | -80 | -80 | -480 | -80 | 6606.9839 | -80 | -80 | -80 | -80
OPENING BALANCE |  |  | 86660.5926 | 86580.5926 | 86500.5926 | 86420.5926 | 86340.5926 | 86260.5926 | 85780.5926 | 85700.5926 | 92307.5765 | 92227.5765 | 92147.5765 | 92067.5765
CLOSING BALANCE |  | 91987.5765 | 86580.5926 | 86500.5926 | 86420.5926 | 86340.5926 | 86260.5926 | 85780.5926 | 85700.5926 | 92307.5765 | 92227.5765 | 92147.5765 | 92067.5765 | 91987.5765
VAT |  | Total | April | May | June | July | August | September | October | November | December | January | February | March
Due on sales |  | 507.6492 | February: 507.6492
Reclaim on purchases |  | 623.2 | February: 623.2

## Year 5
| Unit | Total | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
RECEIPTS |  |  | April | May | June | July | August | September | October | November | December | January | February | March
|  |  | 18.08 | 12.05 | 6.03 | 6.03 |  |  |  |  | 8.26 | 8.26 | 16.52 | 24.78
Harvested timber - larch local firewood - removal of 10% of trees (thin or clearfell) |  | 8701.2926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8701.2926 | 0 | 0 | 0 | 0
TOTAL RECEIPTS |  | 8701.2926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8701.2926 | 0 | 0 | 0 | 0
PAYMENTS
Direct Costs
Maintenance |  | 3116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3116 | 0 | 0 | 0 | 0
Indirect costs
Professional fees |  | 400 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0
Insurance |  | 960 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
TOTAL PAYMENTS |  | 4476 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 3196 | 80 | 80 | 80 | 80
NET CASH FLOW |  | 4225.2926 | -80 | -80 | -80 | -80 | -80 | -480 | -80 | 5505.2926 | -80 | -80 | -80 | -80
OPENING BALANCE |  |  | 91987.5765 | 91907.5765 | 91827.5765 | 91747.5765 | 91667.5765 | 91587.5765 | 91107.5765 | 91027.5765 | 96532.8691 | 96452.8691 | 96372.8691 | 96292.8691
CLOSING BALANCE |  | 96212.8691 | 91907.5765 | 91827.5765 | 91747.5765 | 91667.5765 | 91587.5765 | 91107.5765 | 91027.5765 | 96532.8691 | 96452.8691 | 96372.8691 | 96292.8691 | 96212.8691
VAT |  | Total | April | May | June | July | August | September | October | November | December | January | February | March
Due on sales |  | 435.0646 | February: 435.0646
Reclaim on purchases |  | 623.2 | February: 623.2

## Graphs
Time | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March
Cash | -480 | -560 | -640 | -720 | -800 | -3080 | -960 | 118492.5 | 117712.5 | 117632.5 | 116552.5 | 116472.5 | 116472.5 | 116392.5 | 116312.5 | 116232.5 | 116152.5 | 116072.5 | 115992.5 | 115212.5 | 122269.7926 | 91489.7926 | 85859.7926 | 85079.7926 | 69476.5926 | 69396.5926 | 69316.5926 | 69236.5926 | 69156.5926 | 69076.5926 | 68596.5926 | 68516.5926 | 65320.5926 | 65240.5926 | 65160.5926 | 65080.5926 | 86660.5926 | 86580.5926 | 86500.5926 | 86420.5926 | 86340.5926 | 86260.5926 | 85780.5926 | 85700.5926 | 92307.5765 | 92227.5765 | 92147.5765 | 92067.5765 | 91987.5765 | 91907.5765 | 91827.5765 | 91747.5765 | 91667.5765 | 91587.5765 | 91107.5765 | 91027.5765 | 96532.8691 | 96452.8691 | 96372.8691 | 96292.8691

## P&L
Basic 5 Year P&L
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | 5 year average
Sales | 188732.5 | 8701.2926 | 21835 | 10152.9839 | 8701.2926 | 47624.6138
Capital purchases | 28000 | 31564 | 3116 | 3116 | 3116 | 13782.4
Cost of sales | 4260 | 960 | 1535 | 1710 | 1360 | 1965
Depreciation | 2800 | 5956.4 | 5956.4 | 5956.4 | 5956.4 | 5325.12
Profit (-Loss) | 153672.5 | -29779.1074 | 11227.6 | -629.4161 | -1731.1074 | 26552.0938

## Mensurational data
Mensurational data
Species | Area (from FC stocking map) | Stocking density (tree/ha) | Ave dbh (cm) | Ave top height (m) | Ave tariff # | Ave tree volume (m3) | Standing volume (m3/ha overbark) | % windblown | Total standing volume (m3 overbark)
Pine | 39.7 | 1034 | 20 | 15 | 24 | 0.212 | 219.208 | 50 | 4351.2788
Spruce | 23.1 | 750 | 30 | 24 | 38 | 0.8 | 600 | 15 | 11781
Larch | 15.4 | 887 | 24 | 18 | 30 | 0.39 | 345.93 | 30 | 3729.1254
19861.4042
Timber values
Product (ave across all species) | Roadside value £/t | % of standing volume in woodland | Total volume | Convert to tonnes (1 tonne = 1.2 m3 of timber overbark) | Total value |  |  | Timber prices are average market prices paid at roadside (including harvesting rates).
Chipwood | 28 | 75 | 14896.0531 | 12413.3776 | 347574.5735
Local firewood | 28 | 10 | 1986.1404 | 1655.117 | 46343.2765
Sawlogs | 48 | 15 | 2979.2106 | 2482.6755 | 119168.4252
Total |  | 100 | 19861.4042 | 16551.1702 | 513086.2752
Spruce - clearfell option | [11 empty] | Spruce - small block felling - 2.5ha per block
Product | Roadside value £/t | Harvesting and extraction cost £/t | % of standing volume in woodland | Total volume | Convert to tonnes (1 tonne = 1.2 m3 of timber overbark) | Total roadside timber value | Total harvesting and extraction cost | Total timber profit | Comments |  |  | Product | £/t | % of standing volume in woodland | Volume from 2.5ha blocks | Convert to tonnes (1 tonne = 1.2 m3 of timber overbark) | Total value
Local firewood | 28 | 12 | 10 | 1178.1 | 981.75 | 27489 | 11781 | 15708 | 2m lengths (Dunnet Community Forest sells 1m lengths @ £32/m3) |  |  | Chipwood | 28 | 75% | 1125 | 937.5 | 26250
Chipwood | 28 | 12 | 75 | 8835.75 | 7363.125 | 206167.5 | 88357.5 | 117810 | All chip for external sale (non-log) |  |  | Local firewood | 28 | 10% | 150 | 125 | 3500
Sawlogs | 48 | 12 | 15 | 1767.15 | 1472.625 | 70686 | 17671.5 | 53014.5 | Down to 16cm top diam |  |  | Sawlogs | 48 | 15% | 225 | 187.5 | 9000
Total |  |  | 100 | 11781 | 9817.5 | 304342.5 | 117810 | 186532.5 |  |  |  | Total |  | 100% | 1500 | 1250 | 38750
Pine
Product | £/t | % of standing volume in woodland | Total volume | Convert to tonnes (1 tonne = 1.2 m3 of timber overbark) | Total value
Chipwood | 28 | 75 | 3263.4591 | 2719.5493 | 76147.379
Local firewood | 28 | 10 | 435.1279 | 362.6066 | 10152.9839
Sawlogs | 48 | 15 | 652.6918 | 543.9099 | 26107.6728
Total |  | 100 | 4351.2788 | 3626.0657 | 112408.0357
Larch | [6 empty] | Block felling
Product | £/t | % of standing volume in woodland | Total volume | Convert to tonnes (1 tonne = 1.2 m3 of timber overbark) | Total value |  | Product | £/t | % of standing volume in woodland | Volume from 2.5ha blocks | Convert to tonnes (1 tonne = 1.2 m3 of timber overbark) | Total value
Chipwood | 28 | 75 | 2796.844 | 2330.7034 | 65259.6945 |  | Chipwood | 28 | 75% | 648.6187 | 540.5156 | 15134.4375
Local firewood | 28 | 10 | 372.9125 | 310.7605 | 8701.2926 |  | Fencing product or bars | 28 | 10% | 86.4825 | 72.0688 | 2017.925
Sawlogs | 48 | 15 | 559.3688 | 466.1407 | 22374.7524 |  | Sawlogs | 48 | 15% | 129.7237 | 108.1031 | 5188.95
Total |  | 100 | 3729.1254 | 3107.6045 | 96335.7395 |  | Total |  | 100% | 864.825 | 720.6875 | 22341.3125

## Restocking
Restocking year 5 - spruce area
Area (ha) | 23.1 | Area (ha) | Trees/ha | Number of trees | £/tree planted | Total | Stocking densities
[7 empty] | Broadleaves | 1600
% broadleaved restock | 40% | 9.24 | 1600 | 14784 | 1.05 | 15523.2 | Confier | 2250
% natural regeneration | 40% | 9.24
Open ground | 10% | 2.31 |  |  |  |  | £/tree planted
[6 empty] | 15523.2 | BL | 1.05
[7 empty] | CON | 0.9

## Assumptions
Item | Description
General | Years 1 to 5 - focus on short term restructuring of spruce compartments of woodland.
Harvested timber | Income based on felling as per mensurational data.
Local firewood | Selling of 2m lengths to local market. After year 1 - removal of 10% of larch and pine trees to bring in regular income. Can be through thin or small scale clearfell operation. To be informed by management plan.
Restocking of clearfelled spruce compartments. | Combination of restock mixed broadleaves at 1600/ha at 40% of area, natural regeneration at 40% of area and 10% open ground. Supply and plant each unit broadleaves at @ £1.05.
New forest access track and improvements to Longrigg Road | Based on road engineers report 2020
Turning and timber stacking area | Create new area for turning and timber stacking 600m2 at £25m2
Ground prep/scarifying | Scarify site for planting at £600/ha
Fencing | Maintain boundaries with grazings. Estimate 200 meters Stock proof fencing at £5.00 per meter.
Professional fees | Professional Forester to produce long term plan for value of FGS. Supervison of felling contracts and restocking. Visual tree assessment carried out 4 times in a five year period.
Maintenance | Maintain replanted areas and replace losses - 10% of year 2 cost. Include general maintenance budget of £20 per ha (78.2ha @ £20/ha = £1,564)
Insurance | Average cost would be subject to a specific quote. Includes Public, product, employers and pollution liabilty. Assumed the woodfuel staff may also carry out some chainsaw and low impact forestry work
FGS grant | Paid at £550 per ha for woodland improvement to restrucutre age and species composition at the point of replanting following felling over a three year period.